## Sheet1
P111-2025 B
Public Trust Board Action Log
Action No. | Agenda Item | Date Opened | Description | Owner | Due Date | Progress Notes | RAG Status
TB01-2024 | 5.0 Service Delivery Plan | 2024-02-01 | In response to a question asked from Mrs Gordon regarding productivity on different hospital sites, Mr Campbell advised that the focus had been on specialties across the Trust, but that he would seek to look at data for individual specialties on individual sites. | Mr Campbell | N/A | Per P Watson - At 14 August Mr Campbell advised that his planned meeting with Miss Gordon had to be postponed but he had had a chat with her and will follow up with the information team. Update not available at 28 December given absence of Mr Campbell. Per A Campbell at 24 February 2025 :- Mr Campbell to discuss further with Miss Gordon
TB02-2024 | 12.0 Statutory Function Report | 2024-03-27 | The Chairman thanked Miss Reid for her Report, and asked that the Board’s Corporate Parenting Responsibilities be considered in greater detail at a Board Workshop. | Miss Reid/ Mr Watson | N/A | Per P Watson – was to be on agenda in the Autumn of 2024 although this will now be later in 2025 given other demands on Board time. Per T Reid at 24 February 2025 :- Training provided in summer 2024
TB03-2024 | 12.0 Statutory Function Report | 2024-03-27 | It was agreed that the demands in Social work should be on the agenda for a Strategic Trust Board. | Miss Reid/ Mr Watson | N/A | Per P Watson – was to be on agenda in the Autumn of 2024 although this will now be later in 2025 given other demands on Board time. Per T Reid at 24 February 2025 :- Various inputs on childrens and adult community pressures ; are Trust Board content this can be considered closed ?
TB04-2024 | 8.0 Updated Involvement and Consultation Scheme | 2024-03-27 | It was agreed that the PCC Chair and Chief Executive should be invited to Trust Board in due course. | Mr Watson | N/A | Per P Watson – was to be on agenda in the Autumn of 2024 although this will now be later in 2025 given other demands on Board time. Per P Watson at 24 February 2025 :- PCC attendance tbc for April 2024 meeting
TB05-2024 | 7.0 Proposed Revisions to Trust Standing Orders | 2024-06-12 | Discussion took place in relation to public engagement and it was agreed that Mr Watson would ensure liaison with Mrs Dalzell and Mr Nelson. | Mr Watson | N/A | Per P Watson at January 2025 – Agreed with Chair and B Nelson that to be on April 2025 Trust Board agenda.
TB06-2024 | 4.0 Papers for noting en bloc | 2024-09-12 | In relation to the Annual Progress Report to The Equality Commission, the Chairman noted that some of the graphics, eg Figure 1 on page 4, were very useful, and asked that they be available on Convene. | Mr Watson | N/A | Per P Watson in January 2025 – To now be in the MS Teams repository
TB07-2024 | 7.0 Corporate Plan | 2024-09-12 | It was agreed that there should be a quarterly dashboard showing performance against the Corporate Plan, with formal six monthly reviews by Trust Board.Mr Small enquired if it would be possible to have Trust Key Performance Indicators.Mr Campbell to consider further. | Mr Campbell | N/A | To be considered within the current work ongoing in relation to Trust Board and committee workplan Per P Watson at 24 February 2025 - Mr Campbell has now agreed to the provision of a monthly report on KPIs
TB08-2024 | 7.0 Corporate Plan | 2024-09-12 | Corporate Plan - Mr Watson to arrange a workshop / meeting for Professor Ross, Mr McMullan, Mrs Barron and Mr Campbell to progress. | Mr Watson | N/A | Per P Watson at 24 February 2025 – meeting took place in November 2024
TB09-2024 | 2.0 Action Log | 2024-11-07 | Mr Watson referred the Board to the tabled Action Log. It was agreed that “Green” items be removed, while Mr Watson noted that it was hoped that Convene would facilitate more effective tracking of actions from the Board meetings. | Mr Watson | N/A | Per P Watson at 24 February 2025 - This will be considered further with the roll out of Convene now underway.
TB010-2024 | 7.0 Financial Governance Report | 2024-11-07 | Mrs Edwards indicated that a performance group had been tried at one stage but her suggestion was not that we do not set up another committee as finance was well covered through directorate finance focus groups, QMS and DVP and there was regular reporting to Trust Board. She suggested that the issue could be picked up in the overall review of Trust Board and committee structures if necessary. | Mr Watson | N/A | Per P Watson at 24 February 2025 - Review of Trust Board and committee structures underway.
TB11-2024 | 9.0 Accommodation for Medical Physics | 2024-11-07 | The Chairman noted the comment of Professor Ross regarding the nomenclature of agenda items and papers, which Mr Watson will attend to. | Mr Watson | N/A | Per P Watson at 24 February 2025 - Nomenclature of agenda items and papers now resolved.
TB12-2024 | 10.0 Capital Scheme for Modernisation of Stem Cell Processing Facility | 2024-11-07 | Following discussion, the Board agreed that they would wish to see a report from Mr Porter of the current Trust Estate, indicating its current use (or whether it was vacant). | Mr Porter | N/A | At 10 December 2024 - Mr Porter has confirmed this will be complete within the calendar year 2024 Per D Porter at 24 February 2024 - Work had been developed given changes at BCH. D Porter seeking update.
TB13-2024 | 12.0 Annual Quality Report | 2024-11-07 | The attendance management dashboard should be on Trust Board agendas for noting | Mrs Somerville/ Mr Watson | N/A | Dashboard on TB agenda on 9 January 2025 and also included on latest draft of TB workplan. Per P Watson - on March TB Agenda
TB14-2024 | 12.0 Annual Quality Report | 2024-11-07 | It was agreed that there should be discussion around planned changes to QMS at the Trust Board workshop in December, and how this would sit within the revised Trust Board committee and assurance structures. | Mr Watson | N/A | At January 2025 - Discussion on this moved from December Trust Board workshop to February Trust Board workshop given other demands Per P Watson at 24 February 2025 - Executive Team consideration of QMS has not yet progressed to allow for this to be brought to Trust Board
P001-2025 | 2.0 Action Log | 2025-01-09 | Mr Watson referred the Board to the tabled Action Log.It was agreed that “green” items be removed, while the amber and red items remain on the ongoing action log | Mr Watson | 2025-01-10 | Per P Watson at 24 February 2025 - Feedback provided on 13 February 2025 at Trust Board workshop and incorporate in revised papers.
P002-2025 | 6.0 Progress update on the new Maternity Hospital and the new Children’s Hospital projects. | 2025-01-09 | Miss Gordon indicated that it would be helpful for the Board to have some indication of timescales. Mr Porter noted that timeframes had been outlined in the previous paper, which he would ensure was recirculated to the Board. | Mr Porter | 130225 | Per D Porter on 240225 - Paper with timeframes is to go to Health Committee and will be shared with TB
P003-2025 | 7.0 Updates from Commitees/Standing Report | 2025-01-09 | The Chairman then referred to the section of the agenda for reports from Committees and Standing Reports. The Chairman thanked Mr McVey, as the new Chair of the Assurance Committee who, with Mr Watson, had developed a new format for updating the Board. The Chairman indicated that he considered the new format to be helpful, and asked for feedback to be provided to Mr Watson by the Trust Board members. | Trust Board Members | 130225 | Per P Watson at 24 February 2025 - Feedback provided on 13 February 2025 at Trust Board workshop and incorporated in revised papers.
P004-2025 | 8.0 Papers for noting/approval | 2025-01-09 | Mr McVey noted the reference to job planning.Mrs Edwards indicated that she would ensure an update was provided on job planning to the Trust Board, by Mr Hagan | Mr Hagan | 130225 | Per P Watson at 24 February 2025 - Job Planning update at 31 January 2025 to be circulated w/c 24 February 2025
P005-2025 | 8.0 Papers for noting/approval | 2025-01-09 | The Board noted the above business cases. Query was raised by Board members in relation to the purpose of such papers coming to the Trust Board. Mr Watson advised that in recent days he had been in discussion with a colleague from the Planning, Performance and Informatics team, and that he hoped to be in a position to bring clarity to the Trust Board shortly. | Mr Watson | 130225 | Per P Watson at 24 February 2025 - Paper to issue to TB