## Closed
Public Trust Board Action Log
Action No. | Agenda Item | Date Opened | Description | Owner | Due Date | Progress Notes | RAG Status
TB02-2024 | 12.0 Statutory Function Report | 2024-03-27 | The Chairman thanked Miss Reid for her Report, and asked that the Board’s Corporate Parenting Responsibilities be considered in greater detail at a Board Workshop. | Miss Reid/ Mr Watson | N/A | Per P Watson – was to be on agenda in the Autumn of 2024 although this will now be later in 2025 given other demands on Board time. Per T Reid at 24 February 2025 :- Training provided in summer 2024
TB06-2024 | 4.0 Papers for noting en bloc | 2024-09-12 | In relation to the Annual Progress Report to The Equality Commission, the Chairman noted that some of the graphics, eg Figure 1 on page 4, were very useful, and asked that they be available on Convene. | Mr Watson | N/A | Per P Watson in January 2025 – To now be in the MS Teams repository
TB07-2024 | 7.0 Corporate Plan | 2024-09-12 | It was agreed that there should be a quarterly dashboard showing performance against the Corporate Plan, with formal six monthly reviews by Trust Board.Mr Small enquired if it would be possible to have Trust Key Performance Indicators.Mr Campbell to consider further. | Mr Campbell | N/A | To be considered within the current work ongoing in relation to Trust Board and committee workplan Per P Watson at 24 February 2025 - Mr Campbell has now agreed to the provision of a monthly report on KPIs
TB08-2024 | 7.0 Corporate Plan | 2024-09-12 | Corporate Plan - Mr Watson to arrange a workshop / meeting for Professor Ross, Mr McMullan, Mrs Barron and Mr Campbell to progress. | Mr Watson | N/A | Per P Watson at 24 February 2025 – meeting took place in November 2024
TB11-2024 | 9.0 Accommodation for Medical Physics | 2024-11-07 | The Chairman noted the comment of Professor Ross regarding the nomenclature of agenda items and papers, which Mr Watson will attend to. | Mr Watson | N/A | Per P Watson at 24 February 2025 - Nomenclature of agenda items and papers now resolved.
TB13-2024 | 12.0 Annual Quality Report | 2024-11-07 | The attendance management dashboard should be on Trust Board agendas for noting | Mrs Somerville/ Mr Watson | N/A | Dashboard on TB agenda on 9 January 2025 and also included on latest draft of TB workplan. Per P Watson - on March TB Agenda
P001-2025 | 2.0 Action Log | 2025-01-09 | Mr Watson referred the Board to the tabled Action Log.It was agreed that “green” items be removed, while the amber and red items remain on the ongoing action log | Mr Watson | 2025-01-10 | Per P Watson at 24 February 2025 - Feedback provided on 13 February 2025 at Trust Board workshop and incorporate in revised papers.
P002-2025 | 6.0 Progress update on the new Maternity Hospital and the new Children’s Hospital projects. | 2025-01-09 | Miss Gordon indicated that it would be helpful for the Board to have some indication of timescales. Mr Porter noted that timeframes had been outlined in the previous paper, which he would ensure was recirculated to the Board. | Mr Porter | 130225 | Per D Porter on 240225 - Paper with timeframes is to go to Health Committee and will be shared with TB
P003-2025 | 7.0 Updates from Commitees/Standing Report | 2025-01-09 | The Chairman then referred to the section of the agenda for reports from Committees and Standing Reports. The Chairman thanked Mr McVey, as the new Chair of the Assurance Committee who, with Mr Watson, had developed a new format for updating the Board. The Chairman indicated that he considered the new format to be helpful, and asked for feedback to be provided to Mr Watson by the Trust Board members. | Trust Board Members | 130225 | Per P Watson at 24 February 2025 - Feedback provided on 13 February 2025 at Trust Board workshop and incorporated in revised papers.
P004-2025 | 8.0 Papers for noting/approval | 2025-01-09 | Mr McVey noted the reference to job planning.Mrs Edwards indicated that she would ensure an update was provided on job planning to the Trust Board, by Mr Hagan | Mr Hagan | 130225 | Per P Watson at 27 February 2025 - Job Planning update at 27 February 2025 circulated to Trust Board

## Open
Public Trust Board Action Log | [6 empty] | P125-2025 B
Action No. | Agenda Item | Date Opened | Action | Lead | Due Date | Status/Update
TB01-2024 | 5.0 Service Delivery Plan | 2024-02-01 | Site specific productivity date to be provided | Mr Campbell | N/A | In progress - Mr Campbell progressing
TB03-2024 | 12.0 Statutory Function Report | 2024-03-27 | Social work pressures to be considered at Board | Miss Reid/ Mr Watson | N/A | Complete - Various discussions at Trust Board
TB04-2024 | 8.0 Updated Involvement and Consultation Scheme | 2024-03-27 | PCC Chair and Chief Executive to be invited to Board | Mr Watson | N/A | Outstanding due to agenda pressures
TB05-2024 | 7.0 Proposed Revisions to Trust Standing Orders | 2024-06-12 | Board to consider public engagement | Mr Watson | N/A | Complete - discussed at Board on 3 April
TB09-2024 | 2.0 Action Log | 2024-11-07 | Action Log to be improved | Mr Watson | N/A | Complete - new version of log
TB010-2024 | 7.0 Financial Governance Report | 2024-11-07 | Board to consider need for performance group | Mr Watson | N/A | In progress - Review of Assurance framework underway
TB12-2024 | 10.0 Capital Scheme for Modernisation of Stem Cell Processing Facility | 2024-11-07 | Board to consider report on use of Trust Estate | Mr Porter | N/A | Outstanding - report not received.
TB14-2024 | 12.0 Annual Quality Report | 2024-11-07 | Approach to QMS to be reviewed | Mr Watson | N/A | In progress - QMS proposals to be progressed by Mr Watson and Executive Team
P005-2025 | 8.0 Papers for noting/approval | 2025-01-09 | Approach to Board business case approval role to be reviewed | Mr Watson | 130225 | In progress - Approach to be re--drafted
P006-2025 | 5.0 Action Log | 2025-03-06 | Action Log to be improved | Mr Watson | 2025-04-30 | Complete - new version of log
P007-2025 | 6.0 Chief Executive's Business | 2025-03-06 | Convene functionality to be checked | Mr Watson | 2025-04-30 | Complete - clarity obtained on functionality
P008-2025 | 6.0 Chief Executive's Business | 2025-03-06 | Approach to Sticky Notes / minutes to be determined | Mr Watson | 2025-04-30 | In progress - Approach to Sticky Notes discussed at 3 April Board and proposed approach to come back to TB
P009-2025 | 7.0 Corporate Plan / Service Delivery Plan Report | 2025-03-06 | Revised Corporate Plan to come to Board | Chairman/Mr Campbell | 2025-05-31 | In progress - Due for update in May
P010-2025 | 10.0 Papers for Approval | 2025-03-06 | Agreement to Trust Board workplan | Mr Watson | 2025-04-30 | In progress - Further discussions at 3 April TB and revisions made
P011-2025 | 10.0 Papers for Approval | 2025-03-06 | Feedback on GP daytime access to be fed back | Mr Campbell | 2025-04-30 | Complete - A Campbell confirmed on 10 April that complete