## UPDATE LIVE
Cardiac Surgery Service Action Plan - Last updated 30 June 25 | [5 empty] | RAG STATUS | 0% - to commence | 25% started 50% - good progress 75% - nearly complete | 100% Complete
Review Recommendation No. | Recommendations | Responsibility | No | Required Actions | Date for Completion | Lead for completion | Date of Recent Update | Progress to support RAG Status | RAG Status
1 | The Trust Board should consider whether its current governance arrangements provide for a clear enough picture to be built of clinical risk and patient safety. This recommendation is linked to RCS 1 | Trust Board | 1.1 | The Medical Director will lead on a revision of the Board Assurance Framework to include a review of the function of the Assurance Committee to ensure improved Board oversight of patient safety and clinical governance in the Belfast Trust. This work will be completed in line with Regional Assurance Programme. | 2025-09-30 | C Hagan | 2025-06-18 | Work has commenced External support will be provided to the Trust to help progress this action. | 25%
|  | Patient Safety/Outcomes Group Work Stream 1 Chair - Sam Sloan and Stephen Boyd | 1.2 | Governance and M&M meetings and arrangements in cardiac surgery to be reviewed by the Divisional PSQ Clinical Leads to ensure these are effective. | 2025-06-30 | P Blair/P Glover/B Mullan/S Sloan | 2025-06-30 | Work is ongoing, including weekly Divisional PSQ Lead meetings. Clinical Lead posts x 2 for cardiac surgery service advertised. | 75%
|  |  | 1.3 | M&M Meeting to be held in person - a venue to be identified and booked going forward. Advertisement for Patient Safety and Governance Lead for Cardiac Surgery and Anaesthesia (2 posts) and Cardiothoracic Education Lead planned. | 2025-06-30 | P Blair/P Glover/B Mullan/S Sloan | 2025-06-30 | Face to face venue secured and IT solutions currently being progressed. | 50%
2 | The Trust should create an equivalent Freedom of Speak Up (FTSU) process across the Trust, with an individual specifically appointed to lead it and overseen by a nominated NED. | TRUST WIDE IMPLEMENTATION | 2.1 | Freedom To Speak Up working group to be established with relevant key stakeholders (internal and external) by the end of June 25 | 2025-06-30 | G McKibbin |  | Establishment of group to be progressed
|  |  | 2.2 | HR to issue communications to make staff aware of the current arrangements for speaking up and where to go for support by end June | 2025-06-30 | G McKibbin | 2025-06-18 | Complete and periodic comms to issued | 100%
|  |  | 2.3 | Option paper FTSU to be developed on a proposed FTSU model by end Sept 25 | 2025-09-30 | G McKibbin | 2025-06-30 | Progressing to Trust Board July 25 | 25%
3 | The Trust should deliver a campaign to emphasise the risks to patient safety from poor behaviours in the workplace - see NHS Civility and Respect campaign. Linked to RCS 6 which is complete | TRUST WIDE IMPLEMENTATION | 3.1 | To develop a business case to take forward development of the Trust whistleblowing process which takes account of key benefits of the FTSU process; this will include consideration of implementing a process akin to FTSU | 2025-09-30 | G McKibbin | 2025-06-30 | As above. | 25%
|  |  | 3.2 | Trust to develop multi resources as part of the open, just and learning culture by October 25 | 2025-10-31 | B McConaghy | 2025-06-18 | bespoke appropach for cardiac surgery, ongoing | 25%
|  |  | 3.3 | Safetember' campaign focus by Chris Turner to present 'Civility in healthcare' | 2025-09-01 | B McConaghy | 2025-06-18 | Arrangements in place, ongoing | 75%
|  |  | 3.4 | Establishment of a respect and civility workgroup to take forward a campaign to emphasise the risks to patients safety by the end of June 25 | 2025-06-30 | B McConaghy | 2025-06-18 | Sub group of OJL being formed with chairs identified | 50%
4 | Raising of concerns should be encouraged as an accepted practice within all management and teaching meetings. This recommendation is linked to RCS 2 and 3 | Culture, Support and Communication Group Work Stream 2 Chair - Brian Mullan and Margaret Toner | 4.1 | Workstream 2 to be established to work closely with all professional groups within Cardiac Surgery Unit teams to establish a divisional strategy to address behaviour and culture within the service. | Complete and ongoing | M Toner/B Mullan | 2025-06-18 | 1st meeting took place on the 11th June, ToR/attendees confirmed. Agreed to meet bi-weekly. First meeting focused on the purpose of the group, roles and responsibilities. A workshop was arranged for the next meeting to go through the respect and civility training, which incorporates bystander training, on the 25th June 25. | 75%
|  |  | 4.2 | All staff encouraged and supported to raise concerns at daily safety huddles and team meetings. This has been embedded across all departments within cardiac surgery and is included in the daily safety huddle. Templates in place (See sheet Safety Briefs) | 2025-05-01 | Nathan Tate/ Catherine McQuade | 2025-06-18 | Complete. Ongoing leadership walkabouts
|  |  | 4.3 | As part of encouraging and supporting staff to feel safe to speak up, hold an NMC workshop on 'Raising Concerns and Accountability'. | 2025-06-03 | Nathan Tate/ Catherine McQuade | 2025-06-18 | This workshop was lead by Pamela Craig (Regulation Advisor NI NMC) and was attended by 68 staff across ACCTSS and Surgery at Band 6 and above. Topics discussed included introduction to the NMC, raising concerns, delegation and accountability, documentation and reporting in digital world and impact of professional behaviour on culture. Internal feedback issued following session with return date of 25 June. Further dates in place.Feedback from staff due by 25 June 2025. Further sessions planned.
|  |  | 4.4 | Work closely with the Patient & Client Council to support patients and assist with concerns. | 2025-06-30 | Nathan Tate/ Catherine McQuade | 2025-06-30 | FAQ in place and a further meeting to be confirmed. FAQs approved at Oversight Group on 18 June. Meeting with PCC and corporate Comms 20 June 2025 and FAQs will then be shared with staff. Update 30.06.25 - FAQ now available on PCC website with statement to support the FAQ
|  |  | 4.5 | Senior leadership team to visit CSICU, Theatres and Ward 5A to ensure staff are supported and aware of processes in place to raise concerns. Provide support to staff affected by cultural issues in cardiac surgery. | 2025-05-01 | Nathan Tate/ Catherine McQuade/ Margaret Toner / Stephen Boyd | 2025-06-30 | Ongoing leadership walkabouts. Raising concerns embedded within daily safety huddles. Signposting to existing support and wellbeing services distributed to staff 22.05.25 Specific OH support in place and available until July 25 and can be extended as required 22.05.25. Periodic comms issued re specific OH support, plan to extend after July, staff accessing this support.
|  |  | 4.6 | Management to carry out listening exercise for staff in 5A commencing 4th and 5th June in response to initial feedback following 'Town Hall' events that Ward 5A staff did not feel their voice had been heard during the review stage. Information to be collated with actions identified for feedback to staff before 20 June 25 | 2025-06-20 | Catherine McQuade | 2025-06-30 | Listening event completed. Analysis and feedback ongoing
|  |  | 4.7 | Further listening exercises to be planned before Sept as a means of measuring improvements. This will be agreed within the membership of workstream 2. | 2025-09-30 | M Toner/B Mullan | 2025-06-30 | Listening sessions planned and ongoing | 25%
|  |  | 4.8 | Develop and support staff at all levels with the skills to support others to raise concerns in all settings : 1) The Directorate to develop the appropriate induction/training requirements for newly appointed leadership roles across the MDT. 2) Band 6/7 Development programme is in place for all newly appointed senior nursing. The programme contains managing conflict. | 2025-07-30 | M Toner/B Mullan Nathan Tate/ Catherine McQuade | 2025-06-30 | Induction/training requirements for newly appointed leadership roles (Band 8a/Clinical Leads) across the Directorate to be agreed with Workstream 2 Band 6/7 nursing development programme in place but is currently being reviewed by central nursing to include sign posting to raising concerns, professional accountability and standards. | 50%
|  |  | 4.9 | Put in place arrangements to enable staff to confidentially provide feedback and raise concerns, e.g helpline, email. | 2025-05-29 | M Toner/B Mullan Nathan Tate/ Catherine McQuade | 2025-06-30 | Staff feedback QR code issued 29/05/25 to allow staff to provide comments and suggestions. 38 staff members have accessed QR Code to date. Staff feedback from this exercise will be incorporated into Workstream 2. This is tabled for discussion Meeting No 3 which is due to take place on the 23rd July 25 QR code closed and feedback will be shared within Workstream 2, meeting date 23rd July to help progress communication strategy and to take forward staff feedback. | 50%
|  |  | 4.1 | Workstream 2 to focus on training and development for staff to embed positive values. Consideration of bespoke training such as Civility and Bystander training | 12th June 2025 | M Toner/B Mullan | 2025-06-30 | Civility and bystander training delivered 12 June 2025 to ACCTSS & Surgery SMT & Cardiac Surgery staff as a test. Feedback mechanism in place post training. Further session planned 25 June 2025 | 50%
|  | Medical Directors Office | 4.11 | Work with NIMDTA colleagues (and GMC) to get feedback from trainees to ensure that they feel safe to raise concerns, that any concerns are acted upon effectively and that trainees are getting good training experience in a safe and supportive environment. Ensure trainee welfare is prioritised | 2025-04-01 | C Hagan | 2025-06-30 | Ongoing communication and collaboration with NIMDTA and trainees. Once significant concerns were raised about an individual trainer, immediate steps were taken to ensure trainees were supported through the listening exercise process with DME team. Suitable replacement clinical supervisors were rapidly identified within the team. Educational supervisors for the Foundation doctors (a particularly vulnerable group) were contacted in February (once issues identified) requesting they arrange a supportive meeting with the trainees. ALL BHSCT trainees were sent a short guide on "raising concerns" with the February Trainee newsletter (attached - updated in April). Throughout, there was close communication and collaboration with NIMDTA colleagues (and GMC) to ensure trainee welfare was prioritised
5 | The Cardiac Unit would benefit from greater connectivity with another Unit of similar or larger size. This is to facilitate shared learning, to encourage exchanges and create effective mechanisms to avoid issues or poor practice becoming entrenched. | Work Stream 1 | 5.1 | Develop connections already in place with ROI providers Connections in place with Mater and Blackrock Dublin. | 2025-04-01 | S Sloan/S Boyd | 2025-06-30 | Complete- Connections in place with Mater and Blackrock Dublin; additional work has been done with them around contingency planning
|  |  | 5.2 | Establish connections wth pther cardiac units to share learning and improve. | 2025-06-30 | S Boyd | 2025-06-30 | Ongoing- Co-Director, Surgery to contact St Guys and St Thomas and St Georges Hospitals to establish connections. Other data collected within the department outside of requirements for NICOR will be reviewed in line with these other centres. | 50%
|  |  | 5.3 | Consultants to contribute to NBCC and attend annual conference | 2025-05-01 | S Sloan | 2025-05-01 | Ongoing
|  |  | 5.4 | Establish NICOR data review and report more regularly | 2025-05-01 | S Sloan | 2025-05-01 | Ongong - aim to report quarterly
|  |  | 5.5 | ICNARC to be implemented within CSICU before end of September 2025 | 2025-09-30 | M Toner/ B Mullan | 2025-06-30 | Band 3 Administration post advertised, interviews to take place 27th June 25. Training programme in place once appointment made. | 50%
6 | Deaths on Cardiac Waiting Lists should be regularly analysed and included in formal data reviewed by the Board, Health Authority and also externally. | Work Stream 1 | 6.1 | Improve Board oversight of waiting lists and better capture the impact of long waiting times. The trust aims to review and improve processes within the WLO in relation to how waiting list is monitored and validated for deaths to create a quarterly report. This report will be shared with Oversight Group and Trust Board quarterly. | 2025-06-30 | S Boyd | 2025-06-30 | Administration validation process complete for patients on waiting list. Reduction in waiting times achieved. Next steps will be clinical validation. | 75%
7 | Cardiac Surgeons should regularly review their own outcome data in the form of VLAD or CUSUM plots. This in turn should form part of a broader set of analytical data to monitor effectiveness of the Unit including Waiting List deaths. | Work Stream 1 | 7.1 | Some of this has been done previously but the information was shared through the surgeons meeting previously. Processes to be agreed on how this information is shared across the wider team to incorporate waiting list death information indicated above. Additional KPIs to be set to improve data analysis | 2025-07-31 | S Sloan/S Boyd | 2025-06-30 | Information including return to theatre & infection rates agreed, to be reviewed by Work stream 1. Reporting will include deaths on WL. | 75%
8 | The Trust Board should review how staff are communicated with and steps taken to ensure more opportunities for staff to hear about developments and to contribute their views (focus groups, "town hall" meetings etc.), as well as more time being spent in assessing and thus managing likely reactions to announcements, thus mitigating their effect | Trust Board | 8.1 | Communicate and share findings of review report with staff | 2025-05-01 | Interim Chief Exec/ Chairman | 2025-05-01 | Town hall meetings to be held on 21 May 2025 to communicate and share review report with staff. Follow up Town Hall event planned for August 2025 to feedback to staff on progress.
|  | Work Stream 2 | 8.2 | Ensure that engagement with and involvement of staff is improved through the development of a communication strategy. This recommendation will be brought forward via workstream 2 where representation from all staffing groups will be present for input and agreement (more town hall events, meetings, focus groups etc.). | 2025-09-30 | B Mullan/M Toner | 2025-06-30 | First meeting took place on 11.06.25 with representation from all staffing groups. Second meeting scheduled for 25th June is to test Respect and Civility/Bystander Training. Communication strategy is tabled for meeting No3 which is scheduled for the 23rd July 2025. | 25%
9 | Board knowledge of medical leadership needs to be improved, with more effective oversight by Board committee. The Board should have visibility of all disciplinary processes and internal/external professional reviews against doctors and nurses, to be able to discern patterns and to form a review about improving behaviours, and to ensure that these are not used inappropriately. | Oversight Group | 9.1 | Regular reports all ready in place however Oversight Group to work with central nursing, MDO and HR to agree the collation of information for identification of patterns and further discussion with Trust Board. | 2025-09-30 | T Clinton/P Blair / P Scullin/ B Shaw | 2025-06-30 | Regular reports available for separate professional groups. | 50%
10 | There is a pattern of external reviews not being shared widely with staff, possibly due to the mistaken notion that this will stop enmities developing. Our view is that failure to share such reports has the effect of reducing learning, and inhibits the ability to "move on". | Trust Board | 10.1 | Findings and recommendations to be shared with staff as fully and transparently as possible. | 2025-05-01 | Interim Chief Exec/ Chairman | 2025-05-01 | Complete - a hard copy of the full report was made available to staff at the 'Town Hall' events on 21/22 May 2025
|  | Oversight Group | 10.2 | Action plan and progress reports to be shared with staff to keep them appraised of progress. | 2025-06-20 | T Clinton/P Blair | 2025-06-30 | Ongoing- Action plan and progress to be shared at future engagement events. These dates will be agreed once the action plan is finalised as a live document | 50%
11 | The current leadership team has so much history of being involved in these complex relationships that the only sensible course is to use unconnected (possibly external) individuals to supervise any further disciplinary processes in the Cardiac Unit. | Trust Board | 11.1 | Any further investigation or disciplinary processes will be taken forward following discussion with Executive Team and Trust Board to agree appropriate levels of investigators (whether internal or external) | 2025-09-01 | Trust Board | 2025-06-30 | Trust Board will be seeking further clarity from DCO in relation to this recommendation | 50%
12 | Is the Clinical Director role a sole determinant of escalation, in effect a single point of failure still (this was an RCS ISR Conclusion in 2020) in terms of reflecting concerns or raising issues with higher management? If so, this must be changed to allow more than one point of referral for concerns - a key principle of FTSU. This recommendation is linked to RCS 5 which is closed. | Work Stream 1 | 12.1 | A collective leadership model is in place within the service and is widely known across the Directorate. Gaps in leadership roles and concerns re escalation of issues via this structure to be reviewed in workstream 1 to ensure the Divisions structure is fit for purpose. | 2025-06-30 | S Sloan/S Boyd | 2025-06-30 | Collective Leadership model in place. Leaderships roles have been advertised/ongoing | 50%
13 | Given the behaviours directed at those raising concerns, they should be considered as whistleblowers in order to protect them in law. | Oversight Group and HR | 13.1 | Trust will develop ways which will encourage and support staff to raise concerns and feel protected in doing so. Consideration of adopting good practice from NHS FTSU process. | 2025-07-31 | G McKibbin | 2025-06-30 | Under development - HR will work to continue to ensure staff are protected when raising concerns and Trust plans to strengthen this by adopting learning from the FTSU process including for example FTSU guardians. | 25%
|  |  | 13.2 | Further whistleblowers champions to be identified within the service | 2025-06-30 | T Clinton/P Blair/ G McKibbin | 2025-06-30 | There are whistleblower champions within service but more are required. Communications sent to all staff on 12&19 June reminding staff how they can raise concern, referencing whistleblowing process and advocates. | 25%
14 | Current and ongoing litigation within the Trust should be the subject of a risk conference at a higher level, in order to map the extent of the problem and its likely effects on behaviours. This recommendation is linked to RCS 7 | Trust Board/Oversight Group | 14.1 | Previous risk summits did take place following RCS report in 2020 with DoH, SPPG and PHA colleagues. Consideration to similar approach to be discussed further at with Oversight Group, Trust Board and SPPG/PHA Accountability and Assurance meeting. | 2025-09-01 | Trust Board | 2025-06-30 | The Trust will review its current processes, review purpose and achievements of previous risk summits and agree a process to manage current and ongoing litigation. | 25%
15 | There should be a rapid review of the return-to-work process that was conducted for the former CD, and the impact it caused. | Trust Board | 15.1 | Trust to carry out a review to determine why the return to work was not carried out effectively with the purpose of gaining any learning. | 2025-05-01 | HR | 2025-06-30 | An external HR consultant has been appointed to take this forward. This has commenced. | 50%
RCS 1 | Departmental, and Senior Trust management should reflect on how management structures, and Trust culture and values are perceived by a wide range of staff at all levels. The Trust should seek to improve this perception and properly embed positive values. Support for all staff should be led from the highest level. | Action taken from RCS Report | RCS 1.1 | Meetings with consultant staff to include discussions regarding 'civility saves lives', bullying will not be tolerated, openness and wellbeing was delivered following receipt of the RCS report in 2020. An external facilitator was also appointed to undertake a listening exercise. In addition, the leadership centre was engaged to deliver mentoring and mediation. A Risk Summit outlining the Trusts response to the deliver the action took place with DoH, PHA, HSCB, NIMDTA, PPA, GMC, RQIA and QUB in October 2020. This was followed by a 2nd risk summit in Feb 2021 and 3rd in Jan 2022. | 2025-06-30 | S Boyd/S Sloan | 2025-06-30 | Completed previously. Continue to review/actions ongoing | 75%
|  | HR Leads | RCS 1.2 | Trust undertakes an annual staff survey. The current survey closes at the end of May 25 and report with feedback will be shared July 25 People and culture plans to be a key feature of the Trusts QMS and assurance structure | 2025-07-01 | B McConaghy | 2025-06-30 | Staff Survey completed, results due July 2025 | 75%
|  | ACCTSS & Surgery Leadership Team with HR Partner | RCS 1.3 | Directorate and Divisions to develop people and culture plans in response to staff survey feedback by September 25 | 2025-09-01 | T Clinton, M Toner, S Boyd, J Taggart | 2025-06-30 | Work to commence upon receipt of staff survey results | 25%
RCS 2 | Interactions and communication between the cardiothoracic surgical service management team and clinicians should be reviewed and improved. | Surgical Leadership Team | RCS 2.1 | Prior to the receipt of the report a Cardiac Surgery Leadership team meeting had been established to include managerial, Clinical Director, Co-Director, Chair of Division and representation from ACCTSS management and anaesthetics representation had been established. This group has now been replaced by the Oversight Group which includes HR support, Non-Executive Director, Associate Medical Director and Deputy Director of Nursing. It is planned that information from this group will not only be distributed via work streams but also through a new established cardiothoracic surgical meeting with managerial staff. A schedule of consultant and managerial regular meetings to be established. | 2025-06-30 | S Boyd/S Sloan | 2025-06-30 | Workstream 1 first meeting planned WB 23 June | 25%
RCS 3 | Coaching for managers and leaders should be considered in order to facilitate continuing improvement in management/leadership skills and values. | Work Stream 2 | RCS 3.1 | Ensure that CTS managers and leaders have access and are encouraged to engage in coaching by Sept 25 | 2025-09-30 | B Mullan/M Toner | 2025-06-30 | Ongoing | 25%
|  | Trust Wide Implementation | RCS 3.2 | All leaders and managers will have access to this and there will be further communication and promotion issued as part of the Leadership Academy launch in the autumn. | 2025-09-30 | B McConaghy | 2025-06-30 | In development with launch early October
RCS 4 | A system should be put in place where senior line management formally appraise Clinical Directors at appropriate intervals, ideally on a quarterly basis. | Oversight Group | RCS 4.1 | Chair of Division now in place, regular meetings with CDs established. Interim CD, Mr Paul Blair, in place from May 25. | 2025-05-01 | T Clinton | COMPLETE | Complete
RCS 5 | The consultant team, as a whole, must learn and understand acceptable behaviours in dealing with each other, junior staff and other colleagues, including anaesthetic and nursing staff. Undermining and derogatory comments and behaviour must stop. The Trust management should encourage this learning to support positive change and not use it as a punitive exercise. However, there should be a clear escalation of proportionate sanctions if unacceptable behaviour persists. | Collaborative working with NIMDTA | RCS 5.1 | Following RCS recommendations enhanced monitoring commenced via GMC. The service worked closely with NIMDTA to address all issues and enhanced monitoring was lifted in 2024 (full action plan was in place). The service continues to work closely with NIMDTA in view of recent report. | 2025-05-01 | C Hagan | COMPLETE | Complete with ongoing review
|  | Oversight Group | RCS 5.2 | Communication issued by Medical Director to the consultant team to clarify acceptable behaviours and to support positive change, and to highlight how unacceptable behaviour will be managed. | 2025-05-01 | C Hagan | COMPLETE | Complete with ongoing review
RCS 6 | If necessary, external facilitation should be considered to assist with addressing and rectifying interpersonal issues. | Oversight Group | RCS 6.1 | Mediation NI are currently engaged with staff members to help improve working relationships. | 2025-05-01 | HR | COMPLETE | Ongoing
RCS 7 | The Trust should review the number and appropriateness of internal complaints and grievances being raised by surgeons, at all grades, against other surgeons in the service. | Oversight Group | RCS 7.1 | Further discussion required with MDO. Requires further discussion in current context to include central nursing. | 2025-09-30 | T Clinton/P Blair/P Scullin/ B Shaw | 2025-06-30 | Ongoing | 25%
P143-2025 B

## Tracker
2025-05-01 |  | 2025-06-01
Town Hall Event -staff presented report | complete | NMC Workshop 'Raising Concerns and Accountability' | complete
Wellbeing services in place | complete | Advertisement for Patient Safety & Governances Leads | complete
Specific OH and psychology services | complete | Ensure staff in leadership roles are encouraged to access training | complete
Staff Feedback QR code issued | complete | Workstream 2 First Meeting | complete
Mediation NI in place | complete | Connections and arrangements in place with Patient & Client Council | complete
New Clinical Director Cardiac Surgery appointed | complete | Listening exercise to commence for staff in 5A commencing | complete
|  | Contact made with St Guys/St thomas and St George | complete
|  | A review of all data collated by service (benchmarking/outcomes etc) | 30th
|  | Whistle-blower champions to be identified within the service | 30th
|  | CTS managers to engage in coaching | 30th
|  | Cardiac Surgery Review of Governance structures/arrangements complete | 30th
|  | Overhall of M&M | 30th
|  | Freedom to Speak Up Working Group established | 30th
|  | Establish a respect and civility workgroup | 30th
2025-07-01 |  | 2025-09-01
Consultant and Managerial regular meeting schedule agreed | 01st | Safetember Chris Turner to present Civility in Healthcare | 01st
Feedback from Trust staff survery | 31st | Directorate and Divisions to develop people and culture plans | 01st
|  | Option paper FTSU complete | 30th
|  | Business case for Whistle-Blower service | 30th
|  | ICNARC to be implemented within CSICU | 30th
|  | Regular reports to Trust Board correlating all profesional groups | 30th

## ToR Workstream 2
Terms of Reference Culture, Support and Communication Working Group
NAME | Cardiac Surgery Service Culture, Support and Communication Working Group
PURPOSE | This working group is established to review, develop and implement recommendations associated with the DCO partners External Review of Cardiac Surgery Services and to take forward any other actions that are required to enhance, promote and embed a safe, harmonious working environment for all staff. • To ensure the delivery of a high quality and safe regional cardiothoracic service • To support and enable the creation of a safe, harmonious working environment, where all staff are treated respectfully • To promote effective team working, supported by good communication and responsive line management • To provide updates and assurance to the Cardiac Surgery Steering Group on progress to improve culture and communication supporting the safe delivery of a cardiac surgical service
DUTIES | • To review and implement actions to meet the recommendations from the DCO ‘An independent external review of the Cardiac Surgery Service for BHSCT’. Focus on recommendations 2, 3, 4, and 8 and RCS review recommendation RCS 3. • To ensure multidisciplinary input and collaboration to actions agreed, ensuring progress is monitored and improvements made. • To oversee and ensure regular communications with all staff. • To maintain oversight of any arising risks to the service as a result of the DCO report findings, ensuring all staff are fully supported. • To develop and agree a people and culture plan for the service focusing on improving relationship and team working within the service
AUTHORITY | The group is authorised by the Cardiac Surgery Service Oversight Group to consider any matter within its Terms of Reference. It is authorised to seek information it requires to ensure recommendations can be achieved and supported.
REPORTING | The group will provide updates to the Oversight Group, via the Interim Co- Director and Chair of Division for ACCTSS. An update will be provided to the Oversight Group on a fortnightly basis.
LEAD RESPONSIBILITY | Interim Co-Director and Chair of Division for ACCTSS.
MEMBERSHIP | Chair: Interim Co-Director of ACCTSS – Margaret Toner Chair of Division – Dr Brian Mullan Nathan Tate – Divisional Nurse ACCTSS Catherine McQuade – Divisional Nurse Jennifer Taggart – Senior HR Manager JulieAnne McDonald- Service Manager Theatres Dr Paul Glover – Clinical Director Anaesthetics Cathy Grant – Cardiac Critical Care Scientist Caroline O’Neill – CSICU Lead Nurse Roy Hiles – Cardiac Anaesthetist Joanne Mullan – Ward Manager 5A Joanne Harris – Senior Nurse Ward 5A Joanne Brimston – Theatres Lead Nurse Carolyn McDowell – Theatre Manager Frances Gibson – Senior Nurse Theatres Stephen Uprichard – Cardiac Perfusion Lead Suzanne Moffatt – Cardiac Perfusionist Michael Kerr – Trade Union Representative Cardiac Surgeon – Mark Jones TBC Una Delargy – Senior Administration Carmel Wright – Service Manager Critical Care Maura Quinn – Assistant Service Manager Cardiothoracic
MEETINGS | Quorum: The Chair and at least 9 other members. Frequency of meetings: The group will meet every fortnight which will be reviewed at regular periods Secretarial support: Formal minutes will be taken to include the following: • The names of all present at the meeting, and those from whom apologies have been received • A record of the decisions made and any dissent • Details of how the group was assured and the evidence on which this was based • Details on any issues needing escalation. An action log will be maintained detailing who is responsible for each action Draft minutes and an action log will be issued in advance of each meeting. The agenda and papers will be distributed electronically to members on later than two working days in advance of the date of the meeting.
CONFLICT / DECLARATION OF INTEREST | The Chair shall seek to record any declaration or conflict of interest from members prior to every meeting
REVIEW | The Terms of Reference, membership and operating arrangements will be kept under review
OUTPUT | The group will provide an update and assurance to the Oversight Group following each meeting to ensure the Trust meets its obligations in relation to the delivery of a regional cardiothoracic service Issues/risks will be escalated to the Oversight Group as deemed appropriate

## Oversight Group ToR
Terms of Reference Cardiac Surgery Service Oversight and Reset Group
NAME | Cardiac Surgery Service Oversight and Reset Group
PURPOSE | To ensure the delivery of a high quality and safe regional cardiothoracic service To provide oversight of and support to the independent cardiothoracic review team To manage the reset programme to ensure that any actions or learning identified by the independent review is taken forward To provide updates and assurance to the Chief Executive on the safe delivery of a cardiac surgical service.
DUTIES | Review • To support the independent cardiothoracic review team to ensure the Trust achieves maximum benefit and learning • To undertake benchmarking against other cardiothoracic services to help inform actions and practice • To ensure any actions and/or learning identified by the review/reset team/benchmarking is taken forward Reset • To appoint an independent medical consultant to support the team throughout the reset period • To oversee and ensure regular communications with all staff • To oversee the reintegration of the team and ensure this is managed in a safe and timely way • To maintain oversight of any arising risks to the service as a result of current pressures and ensure these are considered and resolved at the earliest opportunity • To develop and agree a people and culture plan for the service focusing on improving relationship and team working within the service
AUTHORITY | The Group is authorised by the Chief Executive to consider any matter within its Terms of Reference. It is authorised to seek any information it requires from any employee and all employees are required to co-operate with any request made by this group.
REPORTING | The group will provide written updates to the Chief Executive on a fortnightly basis, via the Director of ACCTSS and Surgery. A standing item will be added to each Trust Board meeting agenda, where the Director of ACCTSS and Surgery (or delegated representative) will present a progress update on behalf of the Cardiac Surgery Service Oversight Group. These updates will summarise key actions, risks, assurances, and progress against implementation plans
Accountability and Transparency | To ensure appropriate oversight, the Group will: • Provide a formal report to each Trust Board meeting detailing progress, risks, and escalations. • Maintain an audit trail of decisions and assurance evidence through meeting minutes and an action log. • Ensure visibility and transparency of progress to key stakeholders, including Trust Board, staff and regulators, where appropriate.
LEAD RESPONSIBILITY | Director of ACCTSS and Surgery.
MEMBERSHIP | Chair: and Co-Chair: Interim Director of ACCTSS and Surgery – Tara Clinton/Mr Paul Blair (Consultant Surgeon). Membership: Chair of Division – Sam Sloan Chair of Division – Brian Mullan Deputy Medical Director - Paula Scullin Surgery Co-Director – Stephen Boyd ACCTSS Interim Co-Director – Margaret Toner Divisional Nurse – Catherine McQuade Divisional Nurse – Nathan Tate HR Co-Director – Gladys McKibbin HR Co-Director – Brendan McConaghy Non-Executive Director – Ellen Finlay Central Nursing - Brona Shaw Staff Side Chair – Margaret McKee Regional Branch Secretary RCN – Amanda Smith Deirdre Campbell – Administration
MEETINGS | Quorum: The Chair and at least 5 other members. Frequency of meetings: The Group will meet fortnightly Secretarial support: Formal minutes will be taken to include the following: • The names of all present at the meeting, and those from whom apologies have been received • A record of the decisions made and any dissent • Details of how the group was assured and the evidence on which this was based • Details on any issues needing escalation. An action log will be maintained detailing who is responsible for each action Draft minutes and an action log will be issued in advance of each meeting. The agenda and papers will be distributed electronically to members on later than two working days in advance of the date of the meeting.
CONFLICT / DECLARATION OF INTEREST | The Chair shall seek to record any declaration or conflict of interest from members prior to every meeting
REVIEW | The Terms of Reference, membership and operating arrangements will be kept under review
OUTPUT | The Group will provide an update and assurance to the Chief Executive following each meeting to ensure the Trust meets its obligations in relation to the delivery of a regional cardiothoracic service Issues/risks will be escalated to the Chief Executive as deemed appropriate

## Structure
Oversight Group
(Chairs - T Clinton and P Blair)
ACCTSS & Surgery Leadership Team,
HR, Non-Executive, Deputy MD and external support
Work stream 1
Patient Safety and Governance
(Chairs - S Sloan and S Boyd)
HR, Staff representation CSICU, theatres, Ward 5a, anaesthetists, surgeons, technicians, perfusionists and staff side
Work stream 2
Culture, Communication and Support
(Chairs- B Mullan and M Toner)
HR, staff representation CSICU, theatres, ward 5A, anaesthetists, surgeons, technicians, perfusionists and staff side
External Assurance DoH, SPPG, PHA
External Assurance Governing Bodies GMC, MNC and RQIC
This work steam will focus on Culture, Communication and Support for staff to embed a cohesive, safe, harmonious working environment for all ensuring that recommendations 2, 3, 4, 8 and RCS recommendation 3 is addressed and embedded within the service.
This work stream will focus on Patient Safety and Governance arrangements ensuring that governance structures, participation, engagement and good practice is in place to support a culture of learning and safety for all ensuring recommendations 1, 5, 6, 7 and 12 are addressed
The Oversight Group will be responsible and accountable for the implementation of all recommendations contained within the DCO External Review Report and will work closely and in collaboration with all governing bodies as and when required to ensure the safe, continued delivery of Cardiac Services.
Trust Board

## Safety Templates
| NIGHT TO DAY | SIGN | DAY TO NIGHT | SIGN
NO OF PTS
ACUTELY UNWELL
FALLS RISKS
CONFUSED
SWALLOW ISSUES
INFECTIONS
SPECIAL 1:1
DNARS
UNDER 18
CONCERNS
MEALTIME CO ORDINATOR
GM CHECKS
CD CHECKS
SLUICE
STOCKING UP
PT SAME NAME
FOCUS OF THE MONTH
DEFIB TROLLEY CHECKS