## Key Questions
Answer these questions, before filling in the action plan. This will help you identify actions you could take to improve compliance. This list is not exhaustive, and not every question will apply to you. You should take a proportionate approach based on the needs and resources of your individual authority. In general, you should consider: the points in which delay occurs over the lifetime of a request, whether your established request handling process needs to change, and shortfalls in resource and whether anything can be done about them.
Procedural | Who handles requests? | In an organisation of 22,000 staff with regional services we have 5 x staff handling FOI requests as of June 2025. Prior to that the number was significantly reduced due to staff sickness within the team
| How many requests do they work on at a time? | Usually 30+ cases. Cases include a mix of FOI requests, written and oral Assembly questions, enquiries from MPs, MLAs, Councillors and constituency offices, enquiries from the NI Assembly Health Committee and the Health Minister’s Private Office
| Do they have to prioritise other tasks over handling requests? | Yes, all other enquiries detailed above have shorter turnaround times
| Do you have sufficient staff to handle requests? | Yes, we do now, following a recruitment exercise
| Do you have an established method for handling requests? | Yes
| Does it take a long time to consider whether to withhold information? Why? | However long it takes for a Servce to come back to us, it can be up to 15 days, or can be immediate
| Do you manage requesters' expectations around timescales, to reduce requests for updates which take staff away from handling information requests? | Yes, in our acknowledgement email or holding email if we know we are encountering problems meeting the set timescale
| Do you ever extend the time allowed to respond to a request (where that's appropriate, according to the legislation)? | Yes
| Do you frequently need to consult third parties about the disclosure of information? Does that cause delays? | Yes it does and it occurs as and when necessary - ad hoc
| Do your request handlers regularly discuss the requests they’re working on, to share knowledge and best practice? | Yes at our weekly team meetings. Learnings are typed up and filed off for use at a later date if required
| When you issue a response to an information request, do you receive a lot of secondary correspondence asking for clarification? | Yes, FOI requests are beconing increasingly complex
| Is there a specific type of request that regularly causes you problems? | Those that span multiple Service areas or those that are linked to other processes ie. complaints process or high profile cases that attract media attention
| Have you identified any other procedural issues which are slowing you down? | Yes, most Service Areas have not appointed a lead person to progress replies within their Service. No one senior person is across FOIs which span multiple Service areas. Also, competing pressures within Services and sickness with Services impacts response times
Technical | Do you have a dedicated case management system for handling information requests? | Yes
| How promptly are requests ready to be worked on after they are received by you? | Immediately
| Does your system make it easy to see the information you need to appropriately manage the request? | Yes
| Does the system make it clear when a request is a due? | Yes
| When requests are outside the statutory timeframe, are they flagged, either automatically or in regular reports available to the people involved in handling requests? | Yes, they are flagged in our weekly RAG reports to Directors and Co Directors. These were stood down when we didn’t have enough staff available to run them, but they have been reinstated as of 1 September 2025
| When you have decided that you need to redact information, is the actual process of redacting it straightforward? | Getting staff from within Services to review information can be difficult due to their competing demands. Also depends on the complexity of the information being sought
| Do you have issues with large file sizes when you need to gather large bundles for disclosure, or redact large documents? | No
| Are there any other sticking points caused by the systems you use to handle requests which frequently add time or complexity to the handling of requests? | Our current handling system is not complatible with office 365 and the templates that can be created so we are having to create those manually. We are however moving across to a new recording and monitoring system from 3 November 2025
Organisational | Does the organisation as a whole understand the importance of information rights legislation? | No
| Are staff appropriately trained in recognising and handling information requests (including systems you use and the procedures you follow)? | FOI training is not mandatory for our staff. Training for all staff is available every 6 months. Bespoke training is availabe to Services on an ad hoc basis. Those responsible for compiling responses are aware of the FOI process. We also flag training to Services when we feel they could benefit from this
| Is refresher training available for those who may need it? | Yes
| Is it quick and easy to get responses from elsewhere in the organisation when you need to? | No
| Does oversight of request responses by senior staff, or other people in the organisation, introduce delay? | Yes, due to competing demands, absence or sickness
| Is that delay justifiable – for example, has that oversight identified opportunities to disclose further information or avoided any inappropriate disclosures of information? | It depends on what is happening in the rest of the Organisation and whether Sevices are involved in patient facing care which takes priority
| Are you regularly reporting information rights compliance statistics to senior management boards? Are you flagging and considering the risks posed by falling compliance? | We provide a quarterly FOI report to the Trust's Information Governance Board

## Action Plan
We have designed this template after reviewing numerous action plans sent to us by organisations working to recover from compliance issues. You can tailor the structure to help your organisation. We have populated this template with some example actions. They may not reflect your specific needs but combined with your answers to the key questions, they should give you good starting points to identify actions you can take now to improve your compliance with the statutory timeframes.
| Who is responsible for this plan? | Cathy Shaw
| What is the main objective? | To improve response complainance rates
| What is the timescale? | 2025-12-31
| Action What steps do you need to take? | Impact Why do you need to take this action? | Priority High/med/low | Owner Who is responsible for this action? | Start When will you start? | End When are you aiming to finish work on this action? | Review to be updated regularly - what have you done so far, and what is causing delay? | Completed When did you complete the action?
Procedural - How you handle the requests you receive | STAFF RECRUITMENT: In the short term we temporarily brought in two members of staff from the wider team to help out with the other type of enquiries our team are responsible for. We also brought in an additional two staff temporarily - one via a recruitment agency and one via an internal expression of interest (EOI) to help with those other enquiries and help log some of the backlog of FOI requests | Due to staff sickness we didn’t have enough people to log, process and respond to FOI and Internal Review requests within the legislative timeframes. At one point we had only one staff member carrying this out. We needed more staff so that the one person trainined up in handling FOIs was able to concentrate solely on that while the additional staff brought in could deal with the other type of enquiries our team are responsible for processing. Increased resource, with support for new staff, helped improve overall compliance | High | Bronagh Dalzell | 2025-01-01 | 2025-04-01 | Implemented | 2025-04-01
| STAFF RECRUITMENT: Advertise the initial EOI temporary band 5 post externally on a permanent basis. Advertise a further temporary EOI for an additional band postition to help coordinate work in the office. Recruit temporariily to back fill their substantive position. Advertise the additional higher band on a permanent basis | Given the volume of requests/enquiries our team continues to receive, we now have support to recruit an additional Band 5 and Band 6 post on a permanent basis to help ease the pressure on this Service. Increased resource, with support for new staff, will improve compliance | High | Cathy Shaw | In Process | 2026-04-01 | Permanent Band 5 post advertised externally, awaits shortlisting and appointment. Temporary Band 6 EOI position filled (off ill). Permenent Band 6 post to be drawn up and advertised. | 2025-12-01
| FOI LEADS: Explore identifying a lead person within Directorates/Services with responsibility for progressing FOI requests within their area | Will quickly identify whether an FOI is easy or difficult to answer, if any other Service will need to be involved or if third parties will need to be contacted etc | High | Cathy Shaw | 2025-10-01 | 2025-11-01 | Was taken to Exec Team, responses have been slow. | 2025-11-01
Technical - The tools and resources available to you | NEW SYSTEM: Move across to a new logging and monitoring system | Current system is not compatible with Microsoft 365. The new system generate templates and reports for us therefore reducing handling times. | High | Cathy Shaw | 2025-11-01 | 2025-04-01 | Staff participating in daily training and feedback sessions which is highlighting numerous issues that need tweaked before going live
| RAG REPORT: Re-establish issuing the RAG Report to Directors & Co Directors on a weekly basis | This allows those responsible for responding to FOIs to see how many days they have left to respond or if they are overdue in their response and by how long | High | Cathy Shaw | 2025-09-01 | 2025-09-01 | This continues to be produced weekly | 2025-09-01
Organisational - How your organisation as a whole can support this plan | TRAINING: Offer bespoke training to senior managers within Services or those who help prepare responses to FOI requests | Include this offer of training on a weekly basis via the same email that goes to Directors & Co Directors with the RAG Report | High | Cathy Shaw | 2025-11-01 | Ongoing | Training session took place on 4 November but remains open to other Services on an ad hoc basis | Ongoing
| COMPLIANCE RATES: Communicate to senior staff the risks posed by falling compliance rates, and issues in achieving compliance | An appreciation of the implications of failing to comply, and the causes of non-compliance, can help to focus senior staff on adequately resourcing request handling | High | Cathy Shaw | 2025-10-01 | 2025-10-01 | Highlighted in each weekely RAG report covering email and at training session held on 4 November for FOI Leads | 2025-11-04
| LEGISLATION: Senior staff to be reminded of importance of Freedom of Information legislation via Exec Team and SMT meeting | Support from highest level should help to focus Directrors and Co Directors and filter down through their Services | High | Bronagh Dalzell | 2025-10-01 | 2025-10-01 | Raised at Exec Team on 6 & 13th October (followed up by email) | 2025-10-06