## Closed (hidden)
Public Trust Board Action Log - 16 October 2025
Action No. | Agenda Item | Date Opened | Description | Owner | Due Date | Progress Notes | RAG Status
TB02-2024 | 12.0 Statutory Function Report | 2024-03-27 | The Chairman thanked Miss Reid for her Report, and asked that the Board’s Corporate Parenting Responsibilities be considered in greater detail at a Board Workshop. | Miss Reid/ Mr Watson | N/A | Per P Watson – was to be on agenda in the Autumn of 2024 although this will now be later in 2025 given other demands on Board time. Per T Reid at 24 February 2025 :- Training provided in summer 2024
TB06-2024 | 4.0 Papers for noting en bloc | 2024-09-12 | In relation to the Annual Progress Report to The Equality Commission, the Chairman noted that some of the graphics, eg Figure 1 on page 4, were very useful, and asked that they be available on Convene. | Mr Watson | N/A | Per P Watson in January 2025 – To now be in the MS Teams repository
TB07-2024 | 7.0 Corporate Plan | 2024-09-12 | It was agreed that there should be a quarterly dashboard showing performance against the Corporate Plan, with formal six monthly reviews by Trust Board.Mr Small enquired if it would be possible to have Trust Key Performance Indicators.Mr Campbell to consider further. | Mr Campbell | N/A | To be considered within the current work ongoing in relation to Trust Board and committee workplan Per P Watson at 24 February 2025 - Mr Campbell has now agreed to the provision of a monthly report on KPIs
TB08-2024 | 7.0 Corporate Plan | 2024-09-12 | Corporate Plan - Mr Watson to arrange a workshop / meeting for Professor Ross, Mr McMullan, Mrs Barron and Mr Campbell to progress. | Mr Watson | N/A | Per P Watson at 24 February 2025 – meeting took place in November 2024
TB11-2024 | 9.0 Accommodation for Medical Physics | 2024-11-07 | The Chairman noted the comment of Professor Ross regarding the nomenclature of agenda items and papers, which Mr Watson will attend to. | Mr Watson | N/A | Per P Watson at 24 February 2025 - Nomenclature of agenda items and papers now resolved.
TB13-2024 | 12.0 Annual Quality Report | 2024-11-07 | The attendance management dashboard should be on Trust Board agendas for noting | Mrs Somerville/ Mr Watson | N/A | Dashboard on TB agenda on 9 January 2025 and also included on latest draft of TB workplan. Per P Watson - on March TB Agenda
P001-2025 | 2.0 Action Log | 2025-01-09 | Mr Watson referred the Board to the tabled Action Log.It was agreed that “green” items be removed, while the amber and red items remain on the ongoing action log | Mr Watson | 2025-01-10 | Per P Watson at 24 February 2025 - Feedback provided on 13 February 2025 at Trust Board workshop and incorporate in revised papers.
P002-2025 | 6.0 Progress update on the new Maternity Hospital and the new Children’s Hospital projects. | 2025-01-09 | Miss Gordon indicated that it would be helpful for the Board to have some indication of timescales. Mr Porter noted that timeframes had been outlined in the previous paper, which he would ensure was recirculated to the Board. | Mr Porter | 130225 | Per D Porter on 240225 - Paper with timeframes is to go to Health Committee and will be shared with TB
P003-2025 | 7.0 Updates from Commitees/Standing Report | 2025-01-09 | The Chairman then referred to the section of the agenda for reports from Committees and Standing Reports. The Chairman thanked Mr McVey, as the new Chair of the Assurance Committee who, with Mr Watson, had developed a new format for updating the Board. The Chairman indicated that he considered the new format to be helpful, and asked for feedback to be provided to Mr Watson by the Trust Board members. | Trust Board Members | 130225 | Per P Watson at 24 February 2025 - Feedback provided on 13 February 2025 at Trust Board workshop and incorporated in revised papers.
P004-2025 | 8.0 Papers for noting/approval | 2025-01-09 | Mr McVey noted the reference to job planning.Mrs Edwards indicated that she would ensure an update was provided on job planning to the Trust Board, by Mr Hagan | Mr Hagan | 130225 | Per P Watson at 27 February 2025 - Job Planning update at 27 February 2025 circulated to Trust Board
TB03-2024 | 12.0 Statutory Function Report | 2024-03-27 | Social work pressures to be considered at Board | Miss Reid/ Mr Watson | N/A | Complete - Various discussions at Trust Board
TB05-2024 | 7.0 Proposed Revisions to Trust Standing Orders | 2024-06-12 | Board to consider public engagement | Mr Watson | N/A
TB09-2024 | 2.0 Action Log | 2024-11-07 | Action Log to be improved | Mr Watson | N/A
P006-2025 | 5.0 Action Log | 2025-03-06 | Action Log to be improved | Mr Watson | 2025-04-30 | Complete - new version of log
P007-2025 | 6.0 Chief Executive's Business | 2025-03-06 | Convene functionality to be checked | Mr Watson | 2025-04-30 | Complete - clarity obtained on functionality
P011-2025 | 10.0 Papers for Approval | 2025-03-06 | Feedback on GP daytime access to be fed back | Mr Campbell | 2025-04-30 | Complete - A Campbell confirmed on 10 April that complete
TB12-2024 | 10.0 Capital Scheme for Modernisation of Stem Cell Processing Facility | 2024-11-07 | Board to consider report on use of Trust Estate | Mr Porter | N/A | Complete - On Board agenda for 3 July 2025
P008-2025 | 6.0 Chief Executive's Business | 2025-03-06 | Approach to Sticky Notes / minutes to be determined | Mr Watson | 2025-04-30 | Complete - approach agreed at Board meeting on 5 June 2025
P010-2025 | 10.0 Papers for Approval | 2025-03-06 | Agreement to Trust Board workplan | Mr Watson | 2025-04-30 | Complete - workplan to be kept under review as required.
P013-2025 | 7.0 Chief Executive's Business | 2025-04-30 | Update to be provided on unallocated cases in Childrens Community Services | Ms Weatherall | 2025-07-03 | Complete - Ms Weatherall provided report on 5 June
TB14-2024 | 12.0 Annual Quality Report | 2024-11-07 | Approach to QMS to be reviewed | Mr Watson | N/A | Complete - End of year QMS meetings held in August and September
P009-2025 | 7.0 Corporate Plan / Service Delivery Plan Report | 2025-03-06 | Revised Corporate Plan to come to Board | Chairman/Mr Campbell | 2025-05-31 | Complete -Reviewed at Board on 7 August 2025
P014-2025 | 7.0 Chief Executive's Business | 2025-07-03 | Board asked for update on work already progressed on culture | Mrs Somerville | 2025-09-04 | Complete-Mrs Somerville shared with NEDs on 27 July 2025
P019-2025 | 14. Papers for Oversight and Assurance | 2025-07-03 | M Edwards to ensure balanced update to Minister | Mrs Edwards | 2025-07-03 | Complete - Per M Edwards
P020-2025 | 14. Papers for Oversight and Assurance | 2025-07-03 | T Clinton to address queries re Action Plan | Mrs Clinton | 2025-09-04 | Complete - action superseded by other work on action plan
P017-2025 | 10. Update on Capital Schemes | 2025-07-03 | D Porter to write to DOH re Maternity Hospital seeking permission to proceed with prep works and seek details re DOH review | Mr Porter | 2025-09-04 | Complete - D Porter updated Board on 4 September
P021-2025 | 6. Action Log | 2025-09-04 | Green items to be removed with the exception of P015-2025 to be left as in progress. | Mr Watson | 2025-11-06 | Complete - Actioned in this action log

## Open
Key
Green | On Track for achievement
Amber | On track for achievement with some delay
Red | Off track – intervention needed
Purple | Complete or otherwise to be considered closed
Public Trust Board Action Log at 21 October 2025
Action No. | Agenda Item | Date Opened | Action | Lead | Due Date | Status/Update
TB01-2024 | 5.0 Service Delivery Plan | 2024-02-01 | Site specific productivity date to be provided | Mr Campbell | Was not set when action opened | Complete or otherwise to be considered closed - Separate off line discussions between Acting Chair and Mr Campbell as required.
TB04-2024 | 8.0 Updated Involvement and Consultation Scheme | 2024-03-27 | PCC Chair and Chief Executive to be invited to Board | Mr Watson | Was not set when action opened | Complete or otherwise to be considered closed - Meeting agendas have not been able to accommodate this at this time.
TB010-2024 | 7.0 Financial Governance Report | 2024-11-07 | Board to consider need for performance group | Mr Watson | Was not set when action opened | Complete or otherwise to be considered closed - This matter is being fully considered withn the Review of Assurance framework underway.
P005-2025 | 8.0 Papers for noting/approval | 2025-01-09 | Approach to Board business case approval role to be reviewed | Mr Watson | 2025-02-13 | On track for achievement with some delay - Currently being actively progressed by finance colleagues
P012-2025 | 7.0 Chief Executive's Business | 2025-04-30 | 6 month update on Palliative Care Hub to be provided | Mr McMullan | 2025-10-31 | On track for achievement with some delay - On Board agenda for November 2025
P015-2025 | 7.0 Chief Executive's Business | 2025-07-03 | Board asked that work it had commissioned on Whistleblowing not be delayed | Mrs Somerville | 2025-09-04 | Complete or otherwise to be considered closed - Work ongoing in context of Raising Concerns Task and Finish Group.
P016-2025 | 8.0 Trust Service Delivery Plan | 2025-07-03 | Proposals re service reconfiguration to be brought to Board | Mr Campbell | 2025-09-04 | On track for achievement with some delay- A Campbell brought to Board (confidential) in September 2025 but further work required.
P018-2025 | 11. Updates from Committees | 2025-07-03 | Mr Small to report update to TB following each audit committee meeting | Mr Small/Mrs Cotter | 2025-09-04 | On track for achievement with some delay- On Board agenda for November 2025
P022-2025 | 8. Trust Service Delivery Plan Report | 2025-09-04 | Board asked for update on the financial costs of DNAs | Mr Campbell | 2025-11-06 | On track for achievement - No indication of any delay on due date
P023-2025 | 8. Trust Service Delivery Plan Report | 2025-09-04 | Board asked for follow up with SPPG on comms campaign re DNAs | Mrs Dalzell | 2025-11-06 | Complete or otherwise to be considered closed - Mrs Dalzell advises that SPPG comms team no longer in place.
P024-2025 | 9. Finance Report | 2025-09-04 | Board asked that work on vacancies in social work be in People Report | Ms Weatherall/Mrs Somerville | 2025-11-06 | On track for achievement - No indication of any delay on due date
P157-2025 B