## Sheet1
P185-2026B
Key
Green | On Track for achievement
Amber | On track for achievement with some delay
Red | Off track – intervention needed
Purple | Complete or otherwise to be considered closed
Public Trust Board Action Log at 20 February 2025
Action No. | Agenda Item | Date Opened | Action | Lead | Due Date | Status/Update
P005-2025 | 8.0 Papers for noting/approval | 2025-01-09 | Approach to Board business case approval role to be reviewed | Mr Watson | 2025-02-13 | On track for achievement with some delay - Currently being actively progressed by finance and planning liaising with DOH
P016-2025 | 8.0 Trust Service Delivery Plan | 2025-07-03 | Proposals re service reconfiguration to be brought to Board | Mr Campbell | 2025-09-04 | Complete or otherwise to be considered closed - Planning underway with proposals agreed by Board.
P026-2025 | 4. Chairman's Business | 2025-11-06 | Mr Watson to share questions posed and answers provided to Ms Haughey | Ms Haughey | 2026-01-08 | Complete or otherwise to be considered closed - Correspondence issued on 23 January and copied to Board.
P029-2025 | 4. Chairman's Business | 2025-01-08 | Consideration regarding management of questions to the Board | Mr Watson | 2026-03-05 | On track for achievement with some delay - Public involvement being sought to inform revised process
P30-2025 | 4. Chairman's Business | 2025-01-08 | Response to Mr Smith's correspondence of 30 December 2025 | Mr Watson | 2026-03-05 | Complete or otherwise to be considered closed - Correspondence issued on 23 January and copied to Board.
P31-2025 | 4. Chairman's Business | 2025-01-08 | Response to Ms Haughey further to update on 30 December 2025 | Mr Watson | 2026-03-05 | Complete or otherwise to be considered closed - Correspondence issued on 23 January and copied to Board.
P32-2025 | 4. Chairman's Business | 2025-01-08 | Response to Mr Collins re focal treatments for prostate cancer | Mr Watson | 2026-03-05 | Complete or otherwise to be considered closed - Correspondence issued on 12 January and copied to Board.
P33-2025 | 4. Chairman's Business | 2025-01-08 | Query from Mr Small regarding outstanding mortality reviews | Mr Hagan | 2026-03-05 | On track for achievement - Mr Hagan to update at TB on 5 March
P34-2025 | 7. Chief Executive's Business | 2025-01-08 | Thanks of Board to staff | Dr Armstrong/Mrs Cahalan | 2026-03-05 | Complete or otherwise to be considered closed - Actioned
P35-2025 | 7. Chief Executive's Business | 2025-01-08 | Thanks of Board to staff | Mr McMullan | 2026-03-05 | Complete or otherwise to be considered closed - Actioned
P36-2025 | 7. Chief Executive's Business | 2025-01-08 | Query in relation to performance against 150 day target for clnical trials | Mr McMullan | 2026-03-05 | On track for achievement - Mr Hagan to update at TB on 5 March
P37-2025 | 15. Papers for Oversight | 2025-01-08 | Comments on People Report to be considered in development of People Strategy | Mrs Somerville | 2026-05-01 | On track for achievement - Work ongoing overseen by Culture and Governance Oversight Group
P38-2025 | 16. Ireach Presentation | 2025-01-08 | MoU to be provided to CE | Mr Hagan | 2026-05-01 | Complete or otherwise to be considered closed - Actioned